## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Team | 2025-02-08 | Welcome prompt was not playing automatically when the IVR simulator started | Sprint 1 | Frontend Developer | Functional Defect | Updated frontend logic to trigger welcome prompt on IVR start | 2025-02-09 | Closed | Resolved during UI flow enhancement
2 | QA Team | 2025-02-12 | Keypad buttons were displaying full menu labels instead of simple phone-style digits | Sprint 1 | Frontend Developer | UI Defect | Redesigned keypad to show only numeric dial buttons | 2025-02-13 | Closed | UI updated to resemble actual IVR keypad
3 | Backend Team | 2025-02-18 | Complaint ID input (e.g., cmp202) was not returning any response | Sprint 2 | Backend Developer | Functional Defect | Corrected backend condition handling for complaint lookup IDs | 2025-02-19 | Closed | Complaint flow now works correctly
4 | Backend Team | 2025-02-22 | Refund and cancellation reference IDs were not processed properly by backend | Sprint 2 | Backend Developer | Functional Defect | Added structured lookup handling for refund and cancellation IDs | 2025-02-23 | Closed | All service ID flows validated successfully
5 | QA Team | 2025-03-03 | IVR output included unnecessary passenger name, coach and seat details | Sprint 3 | Data Analyst / Backend Developer | Data Defect | Simplified output structure to display only essential railway service information | 2025-03-04 | Closed | Output aligned to project scope
6 | UI Team | 2025-03-07 | Demo helper text (“Try this for demo”) was visible in interface and audio flow | Sprint 3 | Frontend Developer | UI Defect | Removed helper text from visible UI and speech response | 2025-03-08 | Closed | Improved realism of IVR simulator
7 | QA Team | 2025-03-14 | Login screen was missing in prototype, making access flow incomplete | Sprint 3 | Frontend Developer | Enhancement Defect | Added simple login page before IVR dashboard access | 2025-03-15 | Closed | Improved production-level feel
8 | QA Team | 2025-03-21 | Deployment failed due to dependency conflict in requirements.txt (pydantic issue) | Sprint 4 | Deployment Engineer / Backend Developer | Configuration Defect | Removed conflicting dependency and updated requirements file | 2025-03-22 | Closed | Deployment completed successfully after fix
9 | QA Team | 2025-03-24 | Some test cases failed due to mismatch between expected prompt text and actual output | Sprint 4 | QA Engineer / Backend Developer | Testing Defect | Updated test assertions and aligned prompts with backend responses | 2025-03-25 | Closed | Unit and integration tests passed
10 | QA Team | 2025-03-27 | Live deployed site showed delayed initial loading due to free hosting wake-up delay | Sprint 4 | Deployment Engineer | Performance Defect | Verified issue as hosting-related and documented expected free-tier cold start behavior | 2025-03-28 | Closed | No application logic issue found

## Sheet2
Logical
User Interface
Maintainability
Standards
Others